Plotrol MVP Plan

MVP Goal:
Demonstrate trusted, automated land/asset monitoring using satellite imagery + AI change detection, surfaced through a web GIS dashboard with alerts and auditable evidence.

MVP must prove:

Satellite-based plot change detection works

Geo-AI insights are usable by real users

Alerts + evidence trail can be trusted

Platform is cloud-native and scalable

- MVP Scope (What is IN vs OUT)

What is included in MVP

Functional:

Web-based GIS dashboard

Plot boundary management

Satellite imagery ingestion (optical)

AI-based change detection (batch)

Alert generation & basic workflow

Evidence storage (images + reports)

Immutable audit hash (light PlotVault)

Technical:

Multi-tenant backend (basic)

Secure auth (OAuth)

Cloud object storage

PostgreSQL + PostGIS

Batch AI pipeline (no real-time drones)

Excluded from MVP (Phase 2+)

Mobile app

Drone orchestration

IoT / edge sensors

ZKP proofs (hashing only)

Hyperspectral analytics

Bank / government integrations

- High-Level MVP Architecture

Simplified MVP Stack:

Web GIS (React + Mapbox)

|

API Gateway + Auth

|

Backend Services (Plots, Alerts, Reports)

|

Geo-AI Pipeline (Satellite → AI → Results)

|

PostGIS + Object Storage

|

Audit Hash Ledger

- MVP Delivery Plan & Timeline

Total Duration: 12–14 weeks (Assuming the core development team is full-time)

| Phase | Duration | Deliverables |
| --- | --- | --- |
| Phase 0 – Setup | 1 week | Cloud infra, CI/CD, repo setup |
| Phase 1 – Core Platform | 4 weeks | Backend APIs, auth, PostGIS, storage |
| Phase 2 – Geo-AI MVP | 4 weeks | Satellite ingestion, AI change detection |
| Phase 3 – Web GIS | 3 weeks | Interactive map, alerts, dashboards |
| Phase 4 – Hardening & Demo | 2 weeks | Security, audit hash, pilot demo |

- Resources Needed (Lean MVP Team)

Core Team (5-6 people)

| Role | Count | Notes | FTE Planned |
| --- | --- | --- | --- |
| Solution Architect | 1 | Owns end-to-end design | 0.5 (weekly 20 hours) |
| Backend Engineer | 2 | APIs, workflows, data | 2 |
| Geo-AI / ML Engineer | 1–2 | Satellite + CV models | 0.5 (weekly 20 hours) |
| Frontend Engineer | 1 | Web GIS dashboard | 1 |
| DevOps / Cloud Engineer | 1 | Kubernetes, CI/CD | 0.25 (weekly 10 hours) |
| QA / Test Engineer | 0.5 | Functional + security | 0.5 |

- Cloud Infrastructure Options (AWS vs GCP vs Azure)

Recommended for MVP: AWS

Best balance of Geo, AI, scale, and startup velocity

Why AWS fits Plotrol MVP best

Mature S3 + PostGIS ecosystem

Strong event-driven architecture

GPU availability for AI

Easier global scaling later

AWS MVP Stack

Compute: EKS (Kubernetes)

Storage: S3 (imagery, reports)

DB: RDS PostgreSQL + PostGIS

AI: EC2 GPU (g4dn)

Events: EventBridge / SQS

Auth: Cognito / Keycloak

IaC: Terraform

- MVP Success Metrics (What makes this a “win”)

Detect land changes with >80% precision

Alert generated within 24 hrs of satellite update

GIS dashboard usable by non-technical users

Evidence hash verifiable

System handles 1,000+ plots reliably

- What This MVP Unlocks Next

After MVP validation, you can confidently move to:

Drone automation

Mobile app

Sensor fusion

ZKP-based compliance

Government & bank integrations